## Exemplar - Phase 1
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Marketing & Sales Strategy | Director of Product | Marketing Manager | Marketing Coordinator | Copywriter | Head of Sales | Sales Manager
PHASE 1
Task/Deliverable
1. Create a marketing plan for the new service | C | A | R | C | C | I
2. Write promotional copy | I | A | C | R | I | I
3. Design marketing assets | I | A | R | C | I | I
4. Create a customer outreach and onboarding plan | C | C | I | I | A | R